## Test plan
STT | Test item | Priority | Person in charge | Start date | End date | Out of scope | Risk | Progress
I. | Test case
I.1 | Search weather in your city on Application: https://openweathermap.org/ | High | QuangDT | 2022-02-19 | 2022-02-19 |  |  | Done
- Design testcase
- Write Testcase
- Prepare datatest
I.2 | Search weather in your city by API: https://openweathermap.org/find?q={city name} | High | QuangDT | 2022-02-19 | 2022-02-19 |  |  | Done
- Design testcase
- Write Testcase
- Prepare datatest
II | Test team prepare
| Preparing test tools | High | QuangDT | 2022-02-19 | 2022-02-19 |  |  | Done
- Browser: Chrome, Firefox, Safari, IE
- Postman, Jmeter
- Framework auto test
III | Smoke test
III.1 | Application: | High | QuangDT | 2022-02-19 | 2022-02-19
- Get information weather for your city successfully with input valid
- Get information weather for your city unsuccessfully with input invalid
III.2 | API: | High | QuangDT | 2022-02-19 | 2022-02-19
- Get information weather for your city successfully with parameter valid
- Get information weather for your city unsuccessfully with parameter invalid
IV | Test execution
IV.1 | Application: https://openweathermap.org/ | High | QuangDT | 2022-02-19 | 2022-02-20
- Testing Execution
- Report result
IV.2 | API: https://openweathermap.org/find?q={city name} | High | QuangDT | 2022-02-20 | 2022-02-20
- Testing Execution
- Report result
V | Build automation test framework
| Search weather in your city by API: https://openweathermap.org/find?q={city name} | High | QuangDT | 2022-02-21 | 2022-02-26
- Build framework
- Create Test Script
- Ingration libration report test, CICD
- Run Test
- Check report